## Evidence Requests
Request ID | Control ID | Evidence Requested | Owner | Date Requested | Date Provided | Status | Reviewer | Notes
ER-001 | IA-2 | MFA configuration export + Conditional Access policy | IAM | 2026-09-08 | 2026-09-09 | Ready | GRC | Provided ahead of SAP finalization
ER-002 | AC-6 | RBAC role matrix + PIM activation report | IAM | 2026-09-08 | 2026-09-10 | Ready | GRC
ER-003 | AU-6 | Sentinel correlation rules + audit review log sample | SOC | 2026-09-08 |  | Pending | GRC | SOC compiling 90-day sample
ER-004 | RA-5 | Latest authenticated scan report (infra + web app) | Vuln. Mgmt | 2026-09-08 | 2026-09-11 | Ready | GRC
ER-005 | CM-2 | Terraform baseline export + AWS Config compliance report | Cloud Eng. | 2026-09-08 |  | Gap | GRC | Baseline doc last updated >90 days; refreshing before submission
ER-006 | SC-8 | TLS scan report + certificate inventory | Cloud Eng. | 2026-09-08 | 2026-09-12 | Ready | GRC
ER-007 | SC-28 | KMS key policy + encryption-at-rest report | Cloud Eng. | 2026-09-08 | 2026-09-12 | Ready | GRC
ER-008 | IR-4 | Incident Response Plan + most recent tabletop record | ISSO | 2026-09-08 | 2026-09-13 | Ready | GRC
ER-009 | SI-2 | Patch compliance report (trailing 90 days) | IT Ops | 2026-09-08 |  | Pending | GRC | Awaiting September patch cycle close-out
ER-010 | AC-2 | Account provisioning/deprovisioning log + quarterly access review | IAM | 2026-09-08 | 2026-09-10 | Ready | GRC
Status: Ready = evidence delivered to 3PAO ¦ Pending = owner still compiling ¦ Gap = evidence deficiency, remediation in progress before SAP finalization.