## SAR Findings
SAR Finding ID | Control Ref | Finding Description | Test Method | Risk Rating | Recommended Corrective Action | POA&M Cross-Reference | Status
SAR-001 | AC-6 | Three service accounts hold standing (non-time-bound) administrative privilege rather than PIM-eligible access, contrary to the least-privilege implementation described in the SSP. | Examine + Interview | Moderate | Convert affected accounts to PIM-eligible roles; remove standing assignment. | POA-003 | Open
SAR-002 | AU-2 / AU-6 | Audit log review coverage has a gap on weekends; anomalous activity occurring outside business hours may not be reviewed until the following Monday. | Examine + Test | Moderate | Extend SOC coverage schedule; add automated weekend digest/alerting. | POA-004 | Open
SAR-003 | CP-4 | Contingency plan test (tabletop/failover exercise) is overdue by one quarter against the CP-4 testing cadence in the SSP. | Examine | Moderate | Schedule and execute a contingency plan tabletop/failover exercise; document results. | POA-008 | Open
SAR-004 | SI-7 | Software/firmware integrity monitoring (file integrity monitoring) has not yet been deployed to all in-scope application hosts. | Examine + Interview | Moderate | Deploy file integrity monitoring agent fleet-wide; validate coverage report. | POA-010 | Open
SAR-005 | SA-9 | Annual vendor risk assessment is overdue for one subprocessor with access to system data. | Examine | Low | Complete the annual subprocessor risk questionnaire and update the vendor risk record. | POA-011 | Open
SAR-006 | AU-11 | One log source (SIEM archive) retains audit records for less than the required 12-month period. | Examine | Moderate | Extend archive retention policy to 12 months and confirm via configuration export. | POA-012 | Open
SAR-007 | AT-2 | Security awareness training completion is at 92% against a 100% target for the current cycle. | Examine | Low | Send completion reminders; escalate outstanding staff to their managers. | POA-016 | Open
SAR-008 | CM-3 | One emergency change record is missing a CAB approval timestamp; retroactive ratification was not fully documented at time of testing. | Examine | Low | Backfill the approval documentation and reinforce the emergency-change procedure. | POA-017 | Open
SAR-009 | RA-3 | Cloud Risk Register residual score for one risk was not re-validated after a related control (SC-8) was remediated. | Examine | Low | Re-score the affected risk in the Cloud Risk Register following SC-8 remediation. | POA-018 | Open
Risk Rating fill: yellow = Moderate, green = Low (no High/Critical control-assessment findings in this cycle; scan-based High/Critical findings are tracked in the Vulnerability Register). Each finding's POA&M Cross-Reference is the item it was converted into in 05-POAM/POAM.xlsx -- the remediation tracker of record.

## Summary
Metric | Value
Total SAR Findings (this cycle) | 9
Open | 9
Moderate Risk Rating | 5
Low Risk Rating | 4
Findings Converted to POA&M | 9

## 3PAO Communication Log
Date | Touchpoint Type | Participants | Topic | Outcome / Action Item
2026-09-02 | Kickoff Call | ISSO, GRC, Meridian Lead Assessor | Confirm assessment scope, boundary, and testing window | Scope confirmed against current SSP; testing window set for 2026-09-15 to 2026-09-26
2026-09-08 | Evidence Delivery | GRC, IAM, Cloud Engineering | Deliver first batch of requested evidence (IA-2, AC-6, RA-5, SC-8, SC-28) | 5 of 10 evidence requests marked Ready; see Evidence-Request-Tracker.xlsx
2026-09-10 | SAP Review | ISSO, Meridian Lead Assessor | Review draft Security Assessment Plan: methodology, rules of engagement | SAP approved with minor edits to production-testing notification window
2026-09-15 | Weekly Touchpoint | ISSO, SOC, Meridian Test Team | Testing kickoff status, initial control walkthroughs | No blocking issues; AU-6 evidence sample requested for following week
2026-09-17 | Draft Finding Discussion | ISSO, Cloud Engineering, Meridian Test Team | Informal discussion of AC-6 and CP-4 draft observations | KTech concurred with both observations; remediation planning started ahead of SAR
2026-09-22 | Weekly Touchpoint | ISSO, GRC, Meridian Test Team | Mid-assessment status check; remaining evidence gaps | CM-2 baseline evidence refreshed and delivered; testing on schedule
2026-09-26 | Testing Close-Out | ISSO, Meridian Lead Assessor | Confirm all testing activities complete; align on SAR timeline | SAR draft expected 2026-10-03; no unresolved disputes
2026-10-03 | SAR Review | ISSO, GRC, Meridian Lead Assessor | Review draft SAR for factual accuracy before finalization | Findings SAR-001 through SAR-009 confirmed accurate; POA&M entries opened
A single point of contact (ISSO) is present on every touchpoint to avoid conflicting answers to the 3PAO, per the coordination practices in Assessment-Readiness.md.