## POAM
POA&M ID | Weakness / Finding | Source | Control ID | Severity | Asset | Owner | Detection Date | Scheduled Completion | Days Open | Days Until Due | Status | Milestones / Remediation Plan | Evidence of Closure | Snapshot (As-Of) Date -> | 2026-09-21
POA-001 | Unsupported TLS 1.0/1.1 cipher accepted on load balancer | Scan | SC-8/SC-13 | High | prod-lb-01 | Cloud Engineering | 2026-08-05 | 2026-09-04 | 47 | -17 | Remediation | Disable legacy ciphers in listener policy; validate via TLS rescan.
POA-002 | Missing critical OS security patch (kernel) | Scan | SI-2 | High | app-tier ASG | IT Operations | 2026-08-10 | 2026-09-09 | 42 | -12 | Remediation | Patch via maintenance window; validate via rescan.
POA-003 | Excessive standing privilege on 3 service accounts | Assessment | AC-6 | Moderate | IAM | IAM Team | 2026-07-01 | 2026-09-29 | 82 | 8 | Open | Convert to PIM-eligible roles; remove standing assignment.
POA-004 | Audit log review gap for weekends | Assessment | AU-2/AU-6 | Moderate | Sentinel | SOC | 2026-07-15 | 2026-10-13 | 68 | 22 | Validation | Extend SOC coverage schedule; add automated weekend digest.
POA-005 | S3 bucket policy allows overly broad internal principal | Scan | AC-3 | Moderate | object storage | Cloud Engineering | 2026-08-01 | 2026-10-30 | 51 | 39 | Open | Tighten bucket policy to least-privilege principals.
POA-006 | Container base image missing latest security patches | Scan | SI-2 | Moderate | CI/CD registry | DevSecOps | 2026-08-12 | 2026-11-10 | 40 | 50 | Open | Rebuild from patched base image; add CI gate.
POA-007 | Password policy allows 90-day rotation vs. recommended risk-based approach | Assessment | IA-5 | Low | Entra ID | IAM Team | 2026-06-01 | 2026-11-28 | 112 | 68 | Open | Migrate to risk-based/passwordless authentication policy.
POA-008 | Contingency plan test overdue by one quarter | Assessment | CP-4 | Moderate | N/A | Cloud Engineering | 2026-07-20 | 2026-10-18 | 63 | 27 | Open | Schedule and execute tabletop/failover exercise.
POA-009 | Database instance missing automated minor-version patching | Scan | SI-2 | Moderate | RDS instance | Cloud Engineering | 2026-08-15 | 2026-11-13 | 37 | 53 | Open | Enable automated minor version upgrade window.
POA-010 | Software integrity monitoring (file integrity) not yet deployed | Assessment | SI-7 | Moderate | app servers | Cloud Engineering | 2026-07-25 | 2026-10-23 | 58 | 32 | Open | Deploy file integrity monitoring agent fleet-wide.
POA-011 | Vendor risk assessment overdue for a subprocessor | Assessment | SA-9 | Low | N/A | GRC | 2026-06-10 | 2026-12-07 | 103 | 77 | Open | Complete annual subprocessor risk questionnaire.
POA-012 | Logging retention below 12-month requirement on one log source | Assessment | AU-11 | Moderate | SIEM archive | SOC | 2026-08-01 | 2026-10-30 | 51 | 39 | Open | Extend archive retention policy to 12 months.
POA-013 | Non-critical open port (8080) reachable from internal segment | Scan | SC-7 | Low | internal subnet | Cloud Engineering | 2026-08-20 | 2027-02-16 | 32 | 148 | Open | Close port or document business justification and restrict source.
POA-014 | MFA not enforced for two legacy service accounts | Scan | IA-2 | High | legacy integration | IAM Team | 2026-08-25 | 2026-09-24 | 27 | 3 | Remediation | Migrate to certificate-based auth; retire password fallback.
POA-015 | Backup restoration test result not documented for Q2 | Assessment | CP-9 | Low | backup vault | Cloud Engineering | 2026-07-05 | 2027-01-01 | 78 | 102 | Open | Document Q2 restoration test evidence; schedule Q3 test.
POA-016 | Security awareness training completion at 92% (below 100% target) | Assessment | AT-2 | Low | N/A | GRC | 2026-08-01 | 2026-10-30 | 51 | 39 | Open | Send completion reminders; escalate to managers for outstanding staff.
POA-017 | Change record missing CAB approval timestamp for one emergency change | Assessment | CM-3 | Low | change log | Cloud Engineering | 2026-08-18 | 2026-11-16 | 34 | 56 | Open | Backfill approval documentation; reinforce emergency change procedure.
POA-018 | Risk register residual score not re-validated after control update | Assessment | RA-3 | Low | N/A | GRC | 2026-08-22 | 2026-11-20 | 30 | 60 | Open | Re-score affected risks in Cloud Risk Register following SC-8 remediation.
POA-019 | Weak cipher suite on internal admin console (closed) | Scan | SC-8 | High | admin console | Cloud Engineering | 2026-06-01 | 2026-07-01 | 112 | -82 | Closed | Cipher suite updated and validated. | Rescan confirmed remediation 2026-06-28
POA-020 | Stale privileged account not disabled within SLA (closed) | Scan | AC-2 | High | Entra ID | IAM Team | 2026-05-10 | 2026-06-09 | 134 | -104 | Closed | Account disabled and access review process tightened. | Access review sign-off 2026-06-05
POA-021 | Unencrypted snapshot identified in dev environment (closed) | Scan | SC-28 | Moderate | EBS snapshot | Cloud Engineering | 2026-05-20 | 2026-08-18 | 124 | -34 | Closed | Snapshot re-encrypted with KMS CMK; snapshot policy updated. | KMS policy export 2026-07-30
POA-022 | Missing CAB record for one standard change (closed) | Assessment | CM-3 | Low | change log | Cloud Engineering | 2026-04-01 | 2026-09-28 | 173 | 7 | Closed | Change process retrained; record backfilled and closed. | Change tracker entry CHG-014
Days Open / Days Until Due are calculated against the snapshot (as-of) date in M1 (blue, editable) rather than a volatile TODAY() so the register reads consistently between refreshes. Severity fill: red = High, yellow = Moderate, green = Low; grey rows are Closed.

## Summary
Metric | Value
Total POA&M Items | 22
Open POA&M Items | 18
High-Risk Open Items | 3
Past-Due Open Items | 2
Closed Items (Cumulative) | 4