## Vulnerability Register
Finding ID | Finding | CVSS Score | Severity | Control Ref | Asset | Detection Source | Detection Date | SLA (Days) | Due Date | Days Remaining | Status | Closure / Rescan Date | Severity | SLA Days
V-001 | Unsupported TLS 1.0/1.1 protocol accepted on public load balancer | 7.4 | High | SC-8/SC-13 | prod-lb-01 | Qualys | 2026-08-05 | 30 | 2026-09-04 | -17 | Remediation |  | Critical | 15
V-002 | Missing critical OS security patch (kernel privilege escalation, CVE-class) | 8.1 | High | SI-2 | app-tier ASG | Qualys | 2026-08-10 | 30 | 2026-09-09 | -12 | Remediation |  | High | 30
V-003 | Excessive privilege assigned to service account (standing admin) | 5.9 | Moderate | AC-6 | IAM | Manual Review | 2026-08-01 | 90 | 2026-10-30 | 39 | Open |  | Moderate | 90
V-004 | Audit logging gap identified during control testing (weekend coverage) | 4.3 | Moderate | AU-2/AU-6 | Sentinel | Control Test | 2026-07-15 | 90 | 2026-10-13 | 22 | Validation |  | Low | 180
V-005 | Outdated TLS library version on internal API gateway | 6.8 | Moderate | SC-8 | internal-api-gw | Nessus | 2026-08-12 | 90 | 2026-11-10 | 50 | Open
V-006 | Default credentials present on non-production test instance | 9.1 | Critical | IA-5 | test-env-03 | Qualys | 2026-09-02 | 15 | 2026-09-17 | -4 | Remediation |  | Snapshot (As-Of) Date -> | 2026-09-21
V-007 | Container base image contains 2 known-exploited CVEs | 8.6 | High | SI-2 | CI/CD registry | Trivy (SCA) | 2026-08-20 | 30 | 2026-09-19 | -2 | Remediation
V-008 | Verbose error messages disclose stack trace on application error page | 3.7 | Low | SI-11 | web app | DAST scan | 2026-07-28 | 180 | 2027-01-24 | 125 | Open
V-009 | Missing HTTP security headers (CSP, HSTS) on public endpoint | 4.8 | Moderate | SC-8 | public web app | DAST scan | 2026-08-14 | 90 | 2026-11-12 | 52 | Open
V-010 | Unencrypted EBS snapshot identified in non-production account | 6.2 | Moderate | SC-28 | EBS snapshot | AWS Config | 2026-08-18 | 90 | 2026-11-16 | 56 | Open
V-011 | File integrity monitoring not deployed on 2 application hosts | 5.4 | Moderate | SI-7 | app servers | Internal Assessment | 2026-07-25 | 90 | 2026-10-23 | 32 | Open
V-012 | Weak cipher suite (RC4) enabled on legacy internal admin console | 7.9 | High | SC-8 | admin console | Nessus | 2026-06-01 | 30 | 2026-07-01 | -82 | Closed | 2026-06-28
SLA and Due Date are formula-driven from the Severity → SLA Days lookup table (P1:Q5). Days Remaining is computed against the snapshot (as-of) date in Q7 (blue, editable). Severity fill: red = Critical, orange = High, yellow = Moderate, green = Low; grey rows are Closed.
Formulas:
Due Date = [Detection Date]+[SLA (Days)]

## Summary
Metric | Value
Total Findings | 12
Open (Not Closed) | 11
Critical/High Open | 4
Past SLA (Open) | 4
Closed (Cumulative) | 1