## Risk Register
Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Existing Controls / Mitigations | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score | Risk Owner | Treatment | Status | Next Review
R-01 | Subprocessor (analytics vendor) experiences a data breach affecting shared PHI | Vendor | 4 | 5 | 20 | Annual SOC 2 review; DPA with breach notification clause; data minimization | 2 | 5 | 10 | GRC | Mitigate | Active | 2026-12-01
R-02 | Underlying IaaS (AWS GovCloud) service disruption affects availability | Cloud | 2 | 4 | 8 | Multi-AZ deployment; documented contingency plan; SLA monitoring | 1 | 3 | 3 | Cloud Engineering | Mitigate | Active | 2026-12-01
R-03 | Misconfiguration during rapid deployment introduces a security gap | Operational | 3 | 4 | 12 | IaC policy-as-code gates; peer review on all changes; AWS Config drift detection | 2 | 3 | 6 | Cloud Engineering | Mitigate | Active | 2026-11-15
R-04 | Insider threat: privileged user misuses access to PHI | Operational | 2 | 5 | 10 | Least privilege (AC-6); PIM time-bound access; audit logging (AU-6); background screening (PS-3) | 1 | 5 | 5 | IAM Team | Mitigate | Active | 2026-12-01
R-05 | 3PAO identifies a material weakness jeopardizing authorization timeline | Compliance | 3 | 4 | 12 | Internal readiness review before SAP; evidence request tracker; early gap remediation | 2 | 3 | 6 | GRC | Mitigate | Active | 2026-10-01
R-06 | Unpatched critical vulnerability exploited before SLA remediation | Operational | 3 | 5 | 15 | Monthly authenticated scanning; risk-based SLA triage; compensating WAF/network controls | 2 | 4 | 8 | Vuln. Mgmt Team | Mitigate | Active | 2026-10-15
R-07 | Regulatory change (FedRAMP baseline revision) requires re-mapping of controls | Compliance | 2 | 3 | 6 | Quarterly monitoring of FedRAMP PMO announcements; SSP review cadence | 2 | 2 | 4 | GRC | Accept | Active | 2027-01-01
R-08 | Key personnel departure disrupts ISSO/GRC continuity | Operational | 2 | 3 | 6 | Documented procedures; cross-training; succession planning | 2 | 2 | 4 | GRC | Mitigate | Active | 2026-12-01
R-09 | Third-party API integration introduces an unvetted data flow | Vendor | 3 | 3 | 9 | Vendor risk assessment (SA-9) required before integration approval; network segmentation | 2 | 2 | 4 | GRC | Mitigate | Active | 2026-11-01
R-10 | Cost/resource constraint delays remediation of Moderate findings | Operational | 3 | 2 | 6 | Risk-based prioritization; leadership visibility via ConMon metrics dashboard | 2 | 2 | 4 | GRC | Accept | Active | 2026-12-01
Risk Score = Likelihood x Impact (1-5 scale each, so 1-25). Fill reflects inherent risk band: red >= 15 (High), yellow 8-14 (Moderate), green <= 7 (Low). Residual score reflects risk after existing controls/mitigations.