## Change Tracker
Change ID | Description | Type | Control Ref | Requested By | Risk Assessment | CAB Approval Date | Scheduled Date | Implementation Date | Status | Rollback Plan Ref
CHG-001 | Enforce phishing-resistant MFA for all administrative Conditional Access policies | Standard | IA-2 | IAM Team | Low - improves posture, staged rollout | 2026-08-01 | 2026-08-05 | 2026-08-05 | Implemented | RB-CHG-001
CHG-002 | Patch production load balancer to disable TLS 1.0/1.1 | Standard | SC-8 | Cloud Engineering | Moderate - brief client compatibility check needed | 2026-09-01 | 2026-09-04 |  | Scheduled | RB-CHG-002
CHG-003 | Emergency patch: kernel privilege escalation vulnerability | Emergency | SI-2 | IT Operations | High if unpatched; low deployment risk (vendor-tested patch) | 2026-08-10 | 2026-08-10 | 2026-08-10 | Implemented | RB-CHG-003
CHG-004 | Extend Sentinel audit log retention from 6 to 12 months | Standard | AU-11 | SOC | Low - storage cost increase only | 2026-08-20 | 2026-08-25 | 2026-08-25 | Implemented | RB-CHG-004
CHG-005 | Deploy file integrity monitoring agent fleet-wide | Normal | SI-7 | Cloud Engineering | Moderate - phased rollout to avoid performance impact | 2026-09-15 | 2026-09-22 |  | Approved | RB-CHG-005
CHG-006 | Rotate KMS customer-managed keys (annual rotation) | Standard | SC-28 | Cloud Engineering | Low - automated, no downtime | 2026-09-01 | 2026-09-30 |  | Approved | RB-CHG-006
CHG-007 | Tighten S3 bucket policy to least-privilege internal principals | Standard | AC-3 | Cloud Engineering | Low - validated in staging first | 2026-09-10 | 2026-09-18 |  | Approved | RB-CHG-007
CHG-008 | Update container base image to patched version (registry-wide) | Normal | SI-2 | DevSecOps | Moderate - requires CI/CD pipeline validation | 2026-09-05 | 2026-09-12 | 2026-09-12 | Implemented | RB-CHG-008
Type fill: orange = Emergency (expedited approval per SI-2/IR procedures), yellow = Normal, green = Standard (pre-approved change category). Emergency changes are documented after the fact per CM-3 with retroactive CAB ratification.